## Risk Tests
[5 empty] | BTS1 | BTS2 | SQL1 | SQL2 | IIS1 | IIS2 | SSO
Before | After | Done | Task | Comments
X |  |  | Freeze/Label the source code release
X | X |  | Install and run Microsoft Baseline Security Analyzer | Run the MBSA in all the boxes and allign all the boxes
X |  |  | Firewall | Check the firewall rules for each specific box
X |  |  | Verifying the required Server Roles and Features | Compare the Roles in the Server Manager between the new BizTalk boxes
| X |  | SQL Server Failover testing | Test by moving the SQL cluster application between nodes using Cluster manager. Test also by failing each node in turn.
| X |  | BizTalk Failover testing | Test by moving the BizTalk cluster application between nodes using Cluster manager. Test also by failing each node in turn.
| X |  | SQL server DR Configuration | When the DR kit is available then test the BizTalk databases replica on the DR SQL server using “BizTalk” log shipping.
| X |  | Check the IIS App pool settings between the nodes | Use tools like WebDeploy to compalre the IIS App Pool settings, more information hereç http://www.iis.net/downloads/microsoft/web-deploy
| X |  | Compare the GAC in the BizTalk Boxes with the current one | Run the assemblyscanner tool, command line DBNAME OutputFile assembliesDirectory Where DBNAME is the SQL BizTalk Server Name OutputFile is the text file with all the BTS assemblies assemblyDirectory is the folder with all the assemblies exported For example . "C:\Text.txt" "assembliesDirectory" where
X |  |  | MSDTC | Run the MSDTC Ping and test in all the BizTalk and SQL Server boxes. Run DTCPing from each BizTalk node and perform the SQL cluster failover to cover all the combination between the boxes
| X |  | Atomic test | Run a critical integration test for each BizTalk Boxes

## Security
|  |  | BTS1 | BTS2 | SQL1 | SQL2 | IIS1 | IIS2 | SSO
Done | Task | Comments
| Accounts | Check and compare the BizTalk Accounts credentials for the new environemnt
| Firewall rules | Check the Firewall rules for the new environments
| Check SQL Account settings | Check SQL Account Security Setting
| Check BizTalk Account settings | Check BizTalk Account Security Setting
| Check BizTalk Host settings | Check BizTalk Host Security Setting

## BizTalk Preparation
|  |  | BTS1 | BTS2 | SQL1 | SQL2 | IIS1 | IIS2 | SSO
Done | Task | Comments
Create deployment script files
Prepare the Binding file with new configuration
Get BizTalk configuration files
Export and store the BizTalk MSIs
List the BizTalk connections (Handshake Matrix)
Backup SQL databases
Backup BAM Portal

## PRE BizTalk Installation
|  |  | BTS1 | BTS2 | SQL1 | SQL2 | IIS1 | IIS2 | SSO
Done | Task | Comments
Install and run Microsoft Baseline Security Analyzer
Install updates for Windows (update.microsoft.com)
Verify that all clusters are installed and only needed resources are clustered.
Move TEMP and TMP folders
Move Pagefile: http://support.microsoft.com/kb/307886
Enable IIS
Install WCF for IIS
Configure IIS to NLB or Cluster
Install Network COM+ under application server (roles)
BAM Specific: Install SQL mgmt. Studio (full)
BAM Specific (PRE BizTalk 2013): Install SQL Server 2005 Notification Services
MQ Specific: Install prerequisites for MQSeries Agent
MQSC Specific: Install the MGSC Adapter before you install the WebSphare MQ Client
MQSC Specific: Install WebSphere MQ Client version 7.1 http://biztalkadmin.com/installation-of-the-mqsc-adapter-in-biztalk/
Install .NET Framework 4 and 3.5 SP1
SharePoint Specific: Install SharePoint Services 3.0 SP2
SharePoint Specific: Configure the SharePoint Service
SharePoint Specific: Extend default web sites as a virtual server
Disable shared memory protocol
Join local Administrator Group
Configure RPC Ports
| Check Firewall setting with the Ports Interfaces Handshake Matrix | Document link reference
Check that ports 135, 1433 + defined ports for RPC is open in Firewall
Install and configure MSDTC
Verify DTC with DTC Tester
Disable real-time scanning on Antivirus (or add exceptions)
Disable all unused windows services
Add exceptions to firewall (external and internal)
Configure Event log (size, duration of storage etc).
Registry changes:
Update the LanManWorkstation parameters in the registry
Disable short-filename
DontVerifyRandomDrivers
NTFSDisableLastAccessUpdate
AdditionalDelayedWorkerThreads should be 16
AdditionalCriticalWorkerThreads should be 16
For Secure Intranets: Disable LDAP client signing requirements for computers
NtfsMftZoneReservation 1 if volumes typically store fewer files. 2 or 3 if volumes typically store a moderate number of files. 4 if volumes typically store a large number of files.
MaxWorkItems should be 8192

## BizTalk Installation
|  |  | BTS1 | BTS2 | SQL1 | SQL2 | IIS1 | IIS2 | SSO
Done | Task | Comments
Install BizTalk Server on all of the BizTalk machines
Adapter Pack Specific: Install BizTalk Adapter Pack if requested or required
Install ALL CUs and SP for BizTalk
Adapter Pack Specific: Install BizTalk Adapter Pack CUs and SP
Configure the first server remember to Join SSO (cluster node not physical machine) -Remember to change the names of the default hosts Recommended in-process host is send
Other server must just join group
Perform the Risk Tests
Install Hosts
Configure hosts

## POST BizTalk Installation
|  |  | BTS1 | BTS2 | SQL1 | SQL2 | IIS1 | IIS2 | SSO
Done | Task | Comments
| Configure all hosts according to best practice and naming conventions. | Document link reference
Update the BizTalk configuration files
Update and fix all adapters
Verify that event tracking is set on the pipelines.
Verify windows cluster by clustering the hosts that should be clustered
Run Message Box Viewer
Run BizTalk Best Practice Analyzer
Test and verify that the cluster for hosts works
Set up Performance logging on all machines and point them to a file share
Configure PAL to run these logs once a week (PowerShell and Schedule Task)
Verify environment by using BizTalk Benchmark Wizard
Check Event Log for any errors
Check performance logs with PAL
| Check communication port using Ports Interfaces Handshake Matrix | Document link reference
Check BAM installation
Check BRE Installation
Check ESB Toolkit installation

## SQL Installation
|  |  | BTS1 | BTS2 | SQL1 | SQL2 | IIS1 | IIS2 | SSO
Done | Task | Comments
Install SQL Server
Cluster SQL Server
Add Master Secret Install any updates CUs or SP for SQL Server (MBSA)
Configure parallelism = 1
Enable TCP/IP and Named Pipes
Install Enterprise Single sign On
Configure Enterprise Single Sign on and SQL to work with the windows cluster
Perform the Risk Tests

## POST SQL Installation
|  |  | BTS1 | BTS2 | SQL1 | SQL2 | IIS1 | IIS2 | SSO
Done | Task | Comments
Split log files and data files for the following databases on separate disk: -BizTalkDTADb – separate disks -BizTalkMsgBoxDb – separate disks -BizTalkMgmtDb and SSO – separate disks
Turn off auto update and creation of statistics for the following databases: -BizTalkDTADb -BizTalkMsgBoxDb
Set predefined size and auto growth for all databases
Split files across disks: ALTER DATABASE database_name MODIFY FILE ( NAME = logical_name, FILENAME = 'new_path\os_file_name' );
SQL Agent Jobs - Configure DTA Purge and Cleanup job - Configure Backup job
Prepare clean up environment script: http://gallery.technet.microsoft.com/Powershell-script-to-ed34c5f9 or stored procedure
Perform log shipping from SQL database
Cluster Enterprise Single Sign on to the new SQL Server

## Disaster Recovery
|  |  | BTS1 | BTS2 | SQL1 | SQL2 | IIS1 | IIS2 | SSO
Done | Task | Comments
Configure all hosts according to best practice and naming conventions.
Update and fix all adapters (add the ones the client is going to use)
Verify that event tracking is set on the pipelines.
Verify windows cluster by clustering the hosts that should be clustered
Run Message Box Viewer
Run BizTalk Best Practice Analyzer
Test and verify that the cluster for hosts works
Set up Performance logging on all machines and point them to a file share
Configure PAL to run these logs once a week (PowerShell and Schedule Task)
Verify environment by using BizTalk Benchmark Wizard
Check Event Log for any errors
Check performance logs with PAL

## BizTalk rollout
|  |  | BTS1 | BTS2 | SQL1 | SQL2 | IIS1 | IIS2 | SSO
Done | Task | Comments
Check the state of BizTalk Full Backup • If OK : continue with the migration • If not OK : Make Full backup
Check the state of any singletons • Check if any singletons have no more messages to process. Wait until they are processed or stop the Receive Location which receives the messages which are added to the queue of the singleton
Resume any suspended messages or orchestrations • Resume any suspended orchestrations and/or messages
Stop the BizTalk Application • Disable the Receive Locations • Let BizTalk process running messages/orchestrations (until no more Active orchestratiions exist) • Stop the host instances • Unenlist the orchestrations • Unenlist the Send Port and Send Port Groups
Resume any suspended messages or orchestrations • Resume any suspended messages • Resume any suspended orchestrations • If they cannot be successfully resumed, fix the problem or terminate them

## Power Up
|  |  | BTS1 | BTS2 | SQL1 | SQL2 | IIS1 | IIS2 | SSO
Done | Task | Comments
Delete all third-party testing tools
Clean message box
Clean Tracking database
Do a manual backup (right click message box choose backup)
Update ForceUpdate to value TRUE (messageboxDb -> adm_BackupSettings)
Execute BizTalk Backup SQL Agent Job
Verify BizTalk Administration Guidelines http://social.technet.microsoft.com/wiki/contents/articles/7234.biztalk-administrator-guidelines.aspx
Hand over environment